1.0	Planning Responsibility

1.1	A planning timeline is provided in Table 1-7A for reference.

1.2	The Contest Director is responsible for coordinating the planning for the competition.  Individual tasks should be delegated to relevant chapter committee members / organizing committee to ensure a fair and equal workload.

2.0	Competition Program

2.1	Table 1-7B is a proposed competition schedule for use in planning.    Some variation will be required dependent upon pilot numbers and other factors, but it should provide enough flexibility to cater for typical unplanned events including poor weather.   The golden rule of fly hard early regardless of the weather forecast, is a good one.   Pilots, judges and officials need to be kept informed of all timings and actively herded to reduce wasted time during flyable weather.

2.2	The ACRO contest programme, if used correctly, can reduce the scheduling and task allocation workload on officials.   Pre-load as much data as possible and do some ‘dry runs’ beforehand to become familiar with the process.

2.3	Though difficult, officials should avoid keeping pilots and themselves back late due to administrative needs.   Reduced sleep and missed meals is not conducive to good humor (officials) or peak performance (pilots), and can only be detrimental to flying safety.

3.0	Unknown Sequence Process

3.1	A recurring problem with competitions is the time required to select legal figures, draw flyable sequences, check, select, learn and then fly them in our limited comp timeframe.    The Free Unknown is a great thing as it allows a smart pilot with a lower performance aircraft to design a sequence that can nullify the performance advantage of others.   But the process needs to go smoothly or you will run out of time or end up doing it late at night when the priority should be rest.

3.2	Many methods have been tried over the years to ease the Unknown process.   2014 rules delete free practice during the Known.   This provides the opportunity to do the Free Unknown figure selection the night before competition flying starts, and gives an extra day for pilots to draw sequences and the jury to check and issue them.   See Table 1-7B for a suggested schedule.   This should allow time for the process, provided both the pilots and Jury come prepared.

3.3	While this isn’t ideal, as it breaks from the CIVA process to some degree, it appears a fair compromise.   Other methods such as pre-submitting a selection of figures with your entry or leaving the sequence wholly to the organisers or a non-competing pilot, have too many downside risks to pilots (some obvious, some not so).   Additionally, the art of designing a ‘good’ Free Unknown sequence is one worth learning through experience and observation.

3.4	For 2017 Unknown 1 sequence for Intermediate and below will be provided by the jury and given to pilots with adequate lead time (nominally 6 hours).   That said, lower category pilots should observe the Intermediate, Advanced and Unlimited Free Unknown figure selection and development process so they are at least aware of how it all happens.

Table 1-7A – Planning Timeline

| Comp date | Activity/Task |
| --- | --- |
| -8 weeks | AAC National Committee/AAC State Committee finalise venue selection, obtain airfield owners approval (Event Management Plan), Box survey and local Aeroclub support. |
| -8 weeks | AAC Committee/Chapter Committee appoint CD and CJ. Order trophies, gather perpetual trophies. |
| -7 weeks | CD liaise with CASA re Competition, Approved Persons and Notam, as required. |
| -4 weeks | CD, CJ and Committee appoint Contest Secretary and Scorer |
| -4 weeks | CD, CJ and Committee finalize entry form info, email and post links to website. Entries Open. |
| -4 weeks | Committee book bus hire, follow up local Aero club – catering, hangarage, fuel stocks. |
| -4 weeks | CD or Committee to notify the local CASA field office of the intention to conduct an Aerobatic Contest. |
| -2 weeks | CD stock take Box Markers x 20 Tent pegs x 160 Mallets x 4 Chairs x 15 Umbrellas and straps x 5 Star Pickets x 5 VHF radio x 4 + batteries/chargers UHF radio x 4 Radio Operator shade/table/radio log Computer/ACRO/ARESTI x 2 Printer x 2 4WD Airside vehicle with first response kit |
| -2 weeks | CD CASA/NOTAM follow up. |
| -1 week | Entries Closed. CD and CJ finalise Unknown sequences |

Table 1-7B – Competition Timetable

| Event | Time |  | Description |
| --- | --- | --- | --- |
| NOTAM Current | 0800 dd-mm-yyyy – 1800 dd-mm-yyyy |  | Aerobatics within 2nm of YXXX, SFC – A040, RH CCTS RWYXX, XX and XX. ‘YXXX Advisory’ radio operating IAW CASA EX35/13, aircraft may not be on CTAF frequency. |
| Private Practice | Dd-mm-yyyy – dd-mm-yyyy |  | Not part of competition. Listening watch on CTAF to be maintained by pilots. |
| Registration | From 1300 dd-mm-yyyy |  | Process entries. |
| First Official Briefing | 1800 – 1845 dd-mm-yyyy |  | CD/CJ |
| Unlimited F. Unk1 Figures |  | 1845 – 1945 | Submission of Unk1& Unk2 Figures |
| Advanced F. Unk1 Figures |  | 1945 - 2045 | Submission of Unk1& Unk2 figures. |

dd-mm-yyyy

| Briefing | 0800 – 0830 0830 – 1000 | All participants and officials Registrations Continue |
| --- | --- | --- |
| Advanced Known | 0900 – 1030 | 9 x 10min slots |
| Graduate Known | 1030 – 1130 | 6 x 10 min slots |
| Unlimited Known | 1130 – 1230 | 6 x 10min slots |
| Sportsman Known | 1230 – 1430 | 12 x 10 min slots |
| Intermediate Known | 1430 – 1550 | 8x 10min slots |
| Entry Official Practice | 1550 - 1630 | 4 x 10min slots |

dd-mm-yyyy

| Briefing | 0800 – 0830 | All participants and officials |
| --- | --- | --- |
| Unlimited/Advanced F.Unk1 | 0830 | Pilots post F.Unk1 sequence proposals. |
| Unlimited Free | 0900 - 1000 | 6 x 10min slots |
| Graduate Known 2 | 1000 – 1100 | 6 x 10min slots |
| Advanced Free | 1100 – 1330 | 9 x 10min slots |
| Graduate, Sportsman, Intermediate Unknown | 1330 | Unknown given to pilots. |
| Sportsman Free | 1330 – 1530 | 12 x 10min slots. |
| IntermediateFree | 1530 – 1650 | 8 x 15min slots |
| Entry Known 1 | 1650 – 1730 | 4 x 10min slots |
| UNL/ADV F.Unk1 | 1800 | Pilots nominate F.Unk1 sequence to be flown. |

Friday 8 November 2013

| Briefing | 0800 – 0830 | All participants and officials |
| --- | --- | --- |
| Unlimited/Advanced F.Unk2 | 0830 | Pilots post F.Unk2 sequence proposals. |
| Advanced F.Unk1 | 0900 -1030 | 9 x 10min slots |
| Graduate Unknown | 1030 – 1130 | 6 x 10min slots |
| Unlimited F.Unk1 | 1130 – 1230 | 6 x 10min slots |
| Sportsman Free | 1230 – 1430 | 12 x 10 min slots |
| Intermediate Unknown | 1430 – 1550 | 8 x 10min slots |
| Entry Known 2 | 1550 -1630 | 4 x 10min slots |
| UNL/ADV F.Unk2 | 1800 | Pilots nominate F.Unk2 sequence to be flown. |

dd-mm-yyy

| Briefing | 0800 – 0830 | All participants and officials |
| --- | --- | --- |
| Unlimited F.Unk2 | 0900 -1000 | 6 x 10min slots |
| Advanced F.Unk2 | 1100 – 1230 | 9 x 10min slots |
| 4 Min Free | 1400 - 1500 | 6 x 10min slots |
| Presentation Dinner | 1900 | Venue TBA |

dd-mm-yyyy

| Briefing/Hot-washup | 1000 | All participants and officials |
| --- | --- | --- |
| Any unfinished categories |  |  |
| Pack up box |  |  |
| Clean up |  |  |
| Pay Bills |  |  |
| Depart |  |  |